# Project Plan: Leveraging AI to Answer Customer Questions (Story ID: AUTO-1434)

Objective:
Build an automated pipeline that leverages AI (ChatGPT) to answer customer questions based on enriched, real-time product data.

## System Architecture Overview

Workflow:
Input CSV → Data Cleaning → Website API → JSON (PDP Data) → Clean JSON → Flatten/Summarize Nested JSON → Preprocessor Script → Enriched CSV → ChatGPT Automation (Playwright) → Response Capture → Final Output CSV

## Preprocessor Script Detailed Steps

1. Read Input CSV
   - Load CSV via Pandas.
   - Extract Product ID, Question ID, Question Title, Question Details.

2. Clean Non-UTF Characters (CSV)
   - Remove invalid UTF-8 characters from Question Title and Details.

3. API Data Fetching
   - Fetch JSON product data via Content API.

4. Clean Non-UTF Characters (JSON)
   - Clean invalid UTF-8 characters within JSON text fields.

5. Flatten or Summarize Nested JSON
   - Use pandas.json_normalize or recursive flattening functions.
   - Generate a readable product_context_summary.

6. Data Merging & Enrichment
   - Merge cleaned CSV and flattened/summarized JSON into enriched CSV.

7. Save Enriched CSV
   - Output final enriched dataset ready for ChatGPT automation.

## Playwright Automation

- Use structured prompt templates embedding <product_data> sections.
- Automate ChatGPT interactions using Playwright.
- Capture responses and parse them into final CSV outputs.

## Weekly Timeline (6 Weeks)

Week 1 – Setup and Planning
Week 2 – API Integration & Data Cleaning
Week 3 – Preprocessor Script & Enrichment
Week 4 – Playwright Automation & Testing
Week 5 – UAT and Feedback
Week 6 – Documentation and Sign-Off

## JIRA Stories and Sub-Stories

AUTO-1434-US01: Fetch PDP Data via API

Description: As a developer, I want to fetch PDP-level data via the website content API so that product details are always current.

Acceptance Criteria: API fetch successful for all valid product IDs.

Priority: High, Sprint: Sprint 1, Assignee: Unassigned

AUTO-1434-US02: Preprocessor Script: CSV + JSON Integration

Description: As a preprocessor, I want to clean CSV data, flatten JSON, and merge them so that ChatGPT receives structured product context.

Acceptance Criteria: Enriched CSV includes product_context_summary and cleaned JSON fields.

Priority: High, Sprint: Sprint 2, Assignee: Unassigned

AUTO-1434-US03: ChatGPT Automation via Playwright

Description: As a system, I want to automate ChatGPT using Playwright to feed enriched CSV and capture responses.

Acceptance Criteria: ChatGPT responds with contextually accurate answers for at least 75% of entries.

Priority: High, Sprint: Sprint 3, Assignee: Unassigned

AUTO-1434-US04: Testing, QA, and UAT Validation

Description: As a QA team member, I want to validate API accuracy, ChatGPT consistency, and CSV correctness.

Acceptance Criteria: QA and UAT reports approved with 90%+ test pass rate.

Priority: Medium, Sprint: Sprint 4, Assignee: Unassigned

AUTO-1434-US05: Documentation and Sign-Off

Description: As a stakeholder, I want comprehensive project documentation and final approval.

Acceptance Criteria: Project documentation approved and archived.

Priority: Medium, Sprint: Sprint 5, Assignee: Unassigned

AUTO-1434-SS01: Read Input CSV

Description: Read CSV file using Pandas and extract Product ID, Question ID, Question Title, and Question Details.

Acceptance Criteria: CSV successfully loaded and validated for required columns.

Priority: High, Sprint: Sprint 2, Assignee: Unassigned

AUTO-1434-SS02: Clean Non-UTF Characters (CSV)

Description: Clean non-UTF-8 characters and handle blank Question Title and Question Details.

Acceptance Criteria: No encoding errors and all blank entries handled gracefully.

Priority: High, Sprint: Sprint 2, Assignee: Unassigned

AUTO-1434-SS03: Fetch Product JSON via API

Description: Fetch product JSON (PDP Data) from the content API using Product ID and normalize responses.

Acceptance Criteria: All API calls successful and responses validated.

Priority: High, Sprint: Sprint 2, Assignee: Unassigned

AUTO-1434-SS04: Clean Non-UTF Characters (JSON)

Description: Remove or replace invalid non-UTF-8 characters from fetched JSON data before further processing.

Acceptance Criteria: All JSON text fields validated for UTF compliance.

Priority: High, Sprint: Sprint 2, Assignee: Unassigned

AUTO-1434-SS05: Flatten or Summarize Nested JSON

Description: Flatten or summarize deeply nested product JSONs using pandas.json_normalize or recursive flattening functions.

Acceptance Criteria: Product context summary created for each product record.

Priority: High, Sprint: Sprint 2, Assignee: Unassigned

AUTO-1434-SS06: Merge Cleaned CSV and JSON

Description: Merge flattened JSON and cleaned CSV data into an enriched dataset, adding product_context_summary.

Acceptance Criteria: Merged CSV validated and saved successfully.

Priority: High, Sprint: Sprint 2, Assignee: Unassigned

AUTO-1434-SS07: Build Structured Prompt Template

Description: Design structured ChatGPT prompt including product JSON or summary within <product_data> tags.

Acceptance Criteria: Prompt successfully constructed for each CSV row.

Priority: High, Sprint: Sprint 3, Assignee: Unassigned

AUTO-1434-SS08: Playwright Script for Automation

Description: Automate ChatGPT UI with Playwright to send prompts and capture results.

Acceptance Criteria: Playwright script executes end-to-end successfully.

Priority: High, Sprint: Sprint 3, Assignee: Unassigned

AUTO-1434-SS09: Response Parsing and CSV Output

Description: Extract ChatGPT responses and store them in a structured CSV with product and question IDs.

Acceptance Criteria: Output CSV correctly stores all ChatGPT responses.

Priority: High, Sprint: Sprint 3, Assignee: Unassigned